MIELIKKIX

8-Day Build Sprint — To-Do List

Repo restructure · mielikkix-company-site · shared agent infra · 3 flagship agents · integration testing · deployment

Reality check on the 8-day scope Building the shared infrastructure, restructuring the repo, standing up a new branded site, and shipping 10 fully integrated and deployed AI agents in 8 days is an aggressive target for a small team. This plan front-loads Days 1–8 on the 3 flagship agents (Voice Receptionist, Booking Assistant, Review & Reputation) plus shared infra and the company site — matching your original 30-day plan’s own sequencing. The remaining 7 agents are listed as an immediate Fast-Follow track using the exact same pattern, so nothing is missing — just sequenced realistically.

How to use this list

Work top to bottom. Each day builds on the previous one — don't start Day 4 (first flagship agent) before Day 2's shared agent-core package exists, or you'll rebuild the same LLM/RAG plumbing three times. Tick the Status box as you go.

DAY 1  Foundation & Docs   (ref: Architecture Plan doc)

| # | Task | Status |
| --- | --- | --- |
| 1 | Restructure mielikkix-ai into apps/ + packages/ + infra/ (keep chat-widget/ and dashboard/ live and untouched during the move) | ☐ |
| 2 | Create the mielikkix-company-site repo under github.com/orgs/mielikkix/ | ☐ |
| 3 | Scaffold the site with Palette 1 — Forest & Aurora as the design tokens (see Company Site Design Brief) | ☐ |
| 4 | Add the root CLAUDE.md to both mielikkix-ai and mielikkix-company-site | ☐ |
| 5 | Confirm tech stack for packages/agent-core against your existing backend language | ☐ |

DAY 2  Shared Agent Infrastructure   (ref: agent-core CLAUDE.md)

| # | Task | Status |
| --- | --- | --- |
| 1 | Build packages/agent-core: LLM client wrapper, prompt/tool-calling framework | ☐ |
| 2 | Extend packages/agent-core with memory/RAG utilities (reuse the Chat Widget's existing engine) | ☐ |
| 3 | Build packages/db: schema for agents, bookings, calls, reviews, entitlements | ☐ |
| 4 | Build packages/billing: entitlement check (individual / 3-pack / Full Crew) | ☐ |
| 5 | Build packages/auth: shared session logic reused from the existing backend | ☐ |
| 6 | Smoke-test: one dummy agent module runs end-to-end through agent-core | ☐ |

DAY 3  Company Site Build   (ref: mielikkix-company-site CLAUDE.md)

| # | Task | Status |
| --- | --- | --- |
| 1 | Build site pages: Home, Chat Widget, Force Agents (10-card grid), Pricing, Company | ☐ |
| 2 | Implement the logo concept (geometric fox — Aurora Neon + Antler Gold) | ☐ |
| 3 | Apply component conventions: primary/secondary buttons, card styles, type scale | ☐ |
| 4 | Deploy site to a staging URL | ☐ |
| 5 | Link site CTAs through to app.mielikkix.ai sign-up/login | ☐ |

DAY 4  Flagship Agent 1 — Voice Receptionist   (ref: voice-receptionist CLAUDE.md)

| # | Task | Status |
| --- | --- | --- |
| 1 | Wire telephony provider (call receive/forward + audio streaming) | ☐ |
| 2 | Wire speech-to-text / text-to-speech through agent-core's LLM client pattern | ☐ |
| 3 | Build the call-handling conversation flow (grounded in tenant's info via RAG) | ☐ |
| 4 | Build booking handoff to Booking Assistant | ☐ |
| 5 | Build call summary notification to the business owner | ☐ |
| 6 | Add "Calls" module to dashboard, gated by entitlement | ☐ |

DAY 5  Flagship Agent 2 — Booking Assistant   (ref: booking-assistant CLAUDE.md)

| # | Task | Status |
| --- | --- | --- |
| 1 | Wire calendar integration or internal availability model | ☐ |
| 2 | Build slot lookup + confirmation flow | ☐ |
| 3 | Accept bookings from: Chat Widget, Voice Receptionist handoff, direct dashboard entry | ☐ |
| 4 | Build reminder notifications | ☐ |
| 5 | Add "Bookings" module to dashboard, gated by entitlement | ☐ |

DAY 6  Flagship Agent 3 — Review & Reputation   (ref: review-reputation CLAUDE.md)

| # | Task | Status |
| --- | --- | --- |
| 1 | Wire Google Business Profile + Facebook review sync (scheduled job, not real-time) | ☐ |
| 2 | Build AI reply drafting through agent-core | ☐ |
| 3 | Build human-approval flow + configurable auto-post threshold | ☐ |
| 4 | Add "Reviews" module to dashboard, gated by entitlement | ☐ |

DAY 7  Integration Testing

| # | Task | Status |
| --- | --- | --- |
| 1 | End-to-end test: entitlement gating shows correct modules per plan, for every tenant tier | ☐ |
| 2 | Regression test: Chat Widget still works unaffected by the repo restructure | ☐ |
| 3 | Cross-agent test: Voice Receptionist → Booking Assistant handoff end-to-end | ☐ |
| 4 | Load test on the VPS: concurrent chat conversations | ☐ |
| 5 | Load test on the VPS: concurrent voice calls (this is the outlier — test it on its own) | ☐ |
| 6 | Fix bugs found; re-run failed tests | ☐ |

DAY 8  Deployment & Launch Prep

| # | Task | Status |
| --- | --- | --- |
| 1 | Deploy agent-core + 3 flagship agents to the VPS as a modular process (not 10 containers) | ☐ |
| 2 | Update infra/docker-compose.yml and confirm resource usage (htop/docker stats) stays healthy | ☐ |
| 3 | Deploy mielikkix-company-site to production domain | ☐ |
| 4 | Final smoke test of Chat Widget + 3 agents + dashboard + site in production | ☐ |
| 5 | Mark the remaining 7 agents' Fast-Follow track as started (see below) | ☐ |

FAST-FOLLOW  Remaining 7 Agents (Day 9+, same pattern)   (ref: _template CLAUDE.md)

| # | Task | Status |
| --- | --- | --- |
| 1 | Support Triage | ☐ |
| 2 | Social Media Agent | ☐ |
| 3 | Email Marketing | ☐ |
| 4 | SEO Copywriter | ☐ |
| 5 | Feedback & Survey | ☐ |
| 6 | Loyalty & Re-engagement | ☐ |
| 7 | Quote & Invoice | ☐ |

Each follows the same build → dashboard module → integration test → deploy sequence as Days 4–8, reusing agent-core and the _template/CLAUDE.md checklist.

Companion docs: Mielikkix_10_Agent_Architecture_Plan.docx · Mielikkix_Company_Site_Design_Brief.docx · CLAUDE.md files (one per repo/agent)